## Charter
INTELA – SILVERFIN INTEGRATION · 24-MONTH PROGRAMME MANAGEMENT PLAN
Deloitte Africa ¦ Tax Technology · South Africa · Nigeria · Ghana · Kenya · Tanzania · Uganda · CONFIDENTIAL — internal planning document
PROGRAMME CONTROL
Programme |  | Deloitte Africa — Intela–Silverfin Integration Programme
Sponsor |  | Deloitte Africa Tax & Legal Technology Leadership (to confirm)
Programme Manager |  | To be appointed
Prepared by |  | Tochukwu (El Tee) Owunwanne — Tax Technology, Deloitte Nigeria
PMO contact |  | Sharon Norambuena — Senior Manager: Africa Tax & Legal, Intela PMO
Programme start date |  | 2026-11-01
Programme end date |  | 2028-10-31
Desired deployment date |  | As soon as the integration is approved for use — aligned to each country's Intela deployment plan
Busy season constraint |  | Not applicable
Version / date |  | v2.0 · September 2026
◄ The yellow cell above is the only date you edit. Every start date, finish date, month column and milestone date in this workbook is calculated from it.
PROGRAMME CHARTER
Background |  | Tax practitioners across Deloitte Africa currently move documents, status updates and trial balances between Intela and Silverfin manually, running duplicate workflows with no unified view. This programme establishes a two-way integration so that data captured in Intela flows to Silverfin and back, removing manual effort and creating a single, reliable engagement view.
Objectives |  | 1. Deliver bi-directional trial balance and general ledger synchronisation via the Silverfin SyncAPI. 2. Synchronise documents, engagement status, comments and to-do items between the two platforms. 3. Automate event-based workflows and provide end-to-end monitoring and audit. 4. Roll the solution out across six African countries on a controlled, wave-based schedule.
Scope — in |  | Client and engagement sync · Trial balance and GL sync · Document sync · Status sync · Comments and to-do sync · Workflow automation · Monitoring and audit · Multi-country configuration and rollout across six countries.
Scope — out |  | Changes to core Intela or Silverfin product code · Migration of historical archives beyond an agreed cut-off · New tax-computation logic (delivered separately) · Countries outside the six named markets.
Delivery approach |  | Five stages, applied per region: (1) assessment of tools and build, (2) document sign-off from all stakeholders, (3) architectural build, (4) UAT, (5) deployment. Build runs M1–M19 centrally; UAT and deployment run per region in three waves from M18.
Success criteria |  | Zero manual TB uploads for onboarded engagements · Documents and status reconcile automatically within SLA · A single unified engagement view for practitioners · Successful go-live in all six countries with hypercare exit met.
Indicative effort |  | MVP 12–16 weeks · enterprise build 6–9 months · full multi-country programme up to 24 months. Budget to be confirmed after technical discovery and SyncAPI licensing clarification.
Governance |  | Programme Director / Sponsor · Programme Manager · Solution Architect · Integration Lead · Country SMEs (×6) · Security & Compliance Lead · QA Lead · Change / Training Lead. The steering committee reviews at each phase gate.
Constraints & assumptions |  | Dependent on Silverfin SyncAPI access and the Intela Integration Agent (see the Dependencies tab). Country SMEs available part-time throughout. Data residency and privacy addressed per jurisdiction.
PROGRAMME STATUS — calculated from the Project Plan, Milestones and Risks tabs
Tasks in plan | Completed | In progress | Not started | At risk / on hold | Milestones met | High risks open
70 | 0 | 0 | 70 | 0 | 0 | 6
Added in this version: a dedicated 'Documentation & sign-off' phase (3.1–3.5) and a separate UAT phase per region (12.1–12.4), so the workbook follows the agreed five-step regional approach. Deployment is now its own phase (13.1–13.7).

## Project Plan
PROJECT MANAGEMENT PLAN · INTELA – SILVERFIN INTEGRATION
Milestone → phase → sub-scope. Dates are calculated from the programme start date on the Charter tab.
RESPONSIBILITY
Milestone | Project phase | WBS | Sub-scope / task | Owner (role) | Dependencies | Mo. | Dur. | Start date | End date | Deloitte Tax Technology | Intela PMO / Product | Silverfin (vendor) | Country practice / SMEs | Status | Key deliverable / comments | Phase key (helper — do not delete)
1. Assessment of tools / build per region | 1. Africa Assessment | 1.1 | Programme mobilisation & governance set-up | Programme Manager | — | 1 | 1 | 2026-11-01 | 2026-11-30 | ✓ | ✓ |  |  | Not started | Governance model & charter | 1. Africa Assessment
|  | 1.2 | Stakeholder mapping across the six countries | Business Analyst | 1.1 | 1 | 1 | 2026-11-01 | 2026-11-30 | ✓ |  |  | ✓ | Not started | Stakeholder register | 1. Africa Assessment
|  | 1.3 | Current-state (as-is) process assessment | Business Analyst | 1.1 | 1 | 2 | 2026-11-01 | 2026-12-31 | ✓ |  |  | ✓ | Not started | As-is process maps | 1. Africa Assessment
|  | 1.4 | Country tax-compliance requirements catalogue | Country SMEs | 1.2 | 2 | 2 | 2026-12-01 | 2027-01-31 | ✓ |  |  | ✓ | Not started | Requirements catalogue | 1. Africa Assessment
|  | 1.5 | Silverfin footprint & licensing assessment per region | Solution Architect | 1.3 | 2 | 1 | 2026-12-01 | 2026-12-31 | ✓ |  | ✓ |  | Not started | Footprint & licensing report | 1. Africa Assessment
|  | 1.6 | Assessment report & prioritisation (GATE) | Programme Manager | 1.4,1.5 | 3 | 1 | 2027-01-01 | 2027-01-31 | ✓ | ✓ |  | ✓ | Not started | Assessment sign-off | 1. Africa Assessment
| 2. Technical Discovery | 2.1 | Silverfin API capability review | Solution Architect | 1.5 | 2 | 2 | 2026-12-01 | 2027-01-31 | ✓ |  | ✓ |  | Not started | API capability matrix | 2. Technical Discovery
|  | 2.2 | SyncAPI access request & validation (TB / GL) | Integration Lead | 1.1 | 2 | 2 | 2026-12-01 | 2027-01-31 | ✓ |  | ✓ |  | Not started | SyncAPI access confirmed | 2. Technical Discovery
|  | 2.3 | Intela Integration Agent assessment | Integration Lead | 2.1 | 3 | 1 | 2027-01-01 | 2027-01-31 | ✓ | ✓ |  |  | Not started | Agent assessment note | 2. Technical Discovery
|  | 2.4 | India CTR reference-architecture review | Solution Architect | 2.1 | 3 | 1 | 2027-01-01 | 2027-01-31 | ✓ | ✓ |  |  | Not started | Reference-pattern report | 2. Technical Discovery
|  | 2.5 | TB / Comments / To-Do API validation spike | Integration Engineer | 2.1 | 3 | 2 | 2027-01-01 | 2027-02-28 | ✓ |  | ✓ |  | Not started | Validation findings | 2. Technical Discovery
|  | 2.6 | Target architecture & security design (GATE) | Solution Architect | 2.2,2.3,2.5 | 4 | 1 | 2027-02-01 | 2027-02-28 | ✓ | ✓ |  |  | Not started | Architecture baseline | 2. Technical Discovery
2. Document sign-off from all stakeholders | 3. Documentation & Sign-off | 3.1 | Business requirements document per region | Business Analyst | 1.6,2.6 | 4 | 2 | 2027-02-01 | 2027-03-31 | ✓ |  |  | ✓ | Not started | BRD per country | 3. Documentation & Sign-off
|  | 3.2 | Functional & technical specification (solution design) | Solution Architect | 2.6 | 5 | 2 | 2027-03-01 | 2027-04-30 | ✓ | ✓ |  |  | Not started | FSD / solution design document | 3. Documentation & Sign-off
|  | 3.3 | Data-privacy & residency assessment pack (POPIA, NDPA, DPAs) | Security Lead | 3.1 | 5 | 1 | 2027-03-01 | 2027-03-31 | ✓ |  |  | ✓ | Not started | DPIA pack per jurisdiction | 3. Documentation & Sign-off
|  | 3.4 | Integration approval & security review (Intela & Silverfin) | Integration Lead | 3.2 | 6 | 1 | 2027-04-01 | 2027-04-30 | ✓ | ✓ | ✓ |  | Not started | Vendor integration approval | 3. Documentation & Sign-off
|  | 3.5 | Stakeholder document sign-off — all six countries (GATE) | Programme Manager | 3.3,3.4 | 6 | 1 | 2027-04-01 | 2027-04-30 | ✓ | ✓ |  | ✓ | Not started | Signed-off documentation set | 3. Documentation & Sign-off
3. Architectural build per region | 4. Foundation Integration Layer | 4.1 | Environment provisioning (dev / test / UAT / prod) | DevOps Engineer | 2.6 | 4 | 1 | 2027-02-01 | 2027-02-28 | ✓ |  |  |  | Not started | Environments live | 4. Foundation Integration Layer
|  | 4.2 | Integration Agent deployment & configuration | Integration Lead | 2.6 | 4 | 2 | 2027-02-01 | 2027-03-31 | ✓ | ✓ |  |  | Not started | Agent deployed | 4. Foundation Integration Layer
|  | 4.3 | Authentication, authorisation & secrets management | Security Lead | 4.1 | 5 | 2 | 2027-03-01 | 2027-04-30 | ✓ | ✓ |  |  | Not started | Auth & vault ready | 4. Foundation Integration Layer
|  | 4.4 | Event bus / messaging framework | Integration Engineer | 4.1 | 5 | 2 | 2027-03-01 | 2027-04-30 | ✓ |  |  |  | Not started | Messaging framework | 4. Foundation Integration Layer
|  | 4.5 | Core Silverfin connector (companies / periods / users) | Integration Engineer | 4.3,4.4 | 6 | 2 | 2027-04-01 | 2027-05-31 | ✓ |  | ✓ |  | Not started | Connector v1 | 4. Foundation Integration Layer
|  | 4.6 | Error handling, retry & logging framework | Integration Engineer | 4.5 | 7 | 1 | 2027-05-01 | 2027-05-31 | ✓ |  |  |  | Not started | Resilience framework | 4. Foundation Integration Layer
|  | 4.7 | CI/CD pipeline & infrastructure-as-code | DevOps Engineer | 4.1 | 6 | 2 | 2027-04-01 | 2027-05-31 | ✓ |  |  |  | Not started | CI/CD pipeline | 4. Foundation Integration Layer
|  | 4.8 | Foundation layer integration test (GATE) | QA Lead | 4.5,4.7 | 8 | 1 | 2027-06-01 | 2027-06-30 | ✓ |  |  |  | Not started | Foundation layer ready | 4. Foundation Integration Layer
| 5. Client & Engagement Sync | 5.1 | Client / entity data-model mapping | Data Specialist | 4.5 | 6 | 2 | 2027-04-01 | 2027-05-31 | ✓ |  | ✓ |  | Not started | Mapping specification | 5. Client & Engagement Sync
|  | 5.2 | Client mapping & account-mapping lists | Data Specialist | 5.1 | 7 | 2 | 2027-05-01 | 2027-06-30 | ✓ |  |  | ✓ | Not started | Mapping lists | 5. Client & Engagement Sync
|  | 5.3 | User synchronisation | Integration Engineer | 4.5 | 7 | 1 | 2027-05-01 | 2027-05-31 | ✓ | ✓ |  |  | Not started | User sync build | 5. Client & Engagement Sync
|  | 5.4 | Engagement / period linkage | Integration Engineer | 5.2 | 8 | 1 | 2027-06-01 | 2027-06-30 | ✓ | ✓ |  |  | Not started | Period linkage | 5. Client & Engagement Sync
|  | 5.5 | Client & engagement sync testing (GATE) | QA Lead | 5.3,5.4 | 9 | 1 | 2027-07-01 | 2027-07-31 | ✓ |  |  |  | Not started | Client sync complete | 5. Client & Engagement Sync
| 6. Trial Balance & GL Integration | 6.1 | SyncAPI integration design (TB & GL) | Solution Architect | 2.2,4.8 | 8 | 1 | 2027-06-01 | 2027-06-30 | ✓ |  | ✓ |  | Not started | TB / GL design | 6. Trial Balance & GL Integration
|  | 6.2 | TB import mapping & transformation rules | Data Specialist | 5.2 | 8 | 2 | 2027-06-01 | 2027-07-31 | ✓ |  |  | ✓ | Not started | Transformation rules | 6. Trial Balance & GL Integration
|  | 6.3 | General Ledger synchronisation build | Integration Engineer | 6.1 | 9 | 2 | 2027-07-01 | 2027-08-31 | ✓ |  | ✓ |  | Not started | GL sync build | 6. Trial Balance & GL Integration
|  | 6.4 | TB push Intela → Silverfin build | Integration Engineer | 6.2,6.3 | 10 | 2 | 2027-08-01 | 2027-09-30 | ✓ | ✓ | ✓ |  | Not started | TB sync build | 6. Trial Balance & GL Integration
|  | 6.5 | Account-mapping validation & reconciliation | Data Specialist | 6.4 | 11 | 1 | 2027-09-01 | 2027-09-30 | ✓ |  |  | ✓ | Not started | Reconciliation controls | 6. Trial Balance & GL Integration
|  | 6.6 | TB / GL end-to-end testing (GATE) | QA Lead | 6.4,6.5 | 12 | 1 | 2027-10-01 | 2027-10-31 | ✓ |  |  |  | Not started | TB / GL validated | 6. Trial Balance & GL Integration
| 7. Document Synchronisation | 7.1 | Document taxonomy & metadata mapping | Business Analyst | 5.5 | 10 | 1 | 2027-08-01 | 2027-08-31 | ✓ |  |  | ✓ | Not started | Document taxonomy | 7. Document Synchronisation
|  | 7.2 | Document sync build (documents, schedules, packs) | Integration Engineer | 7.1 | 11 | 2 | 2027-09-01 | 2027-10-31 | ✓ | ✓ |  |  | Not started | Document sync build | 7. Document Synchronisation
|  | 7.3 | Live Export Documents integration | Integration Engineer | 7.2 | 12 | 1 | 2027-10-01 | 2027-10-31 | ✓ |  | ✓ |  | Not started | Live export integrated | 7. Document Synchronisation
|  | 7.4 | Document versioning & retention rules | Security Lead | 7.2 | 12 | 1 | 2027-10-01 | 2027-10-31 | ✓ |  |  |  | Not started | Versioning rules | 7. Document Synchronisation
|  | 7.5 | Document sync testing (GATE) | QA Lead | 7.3,7.4 | 13 | 1 | 2027-11-01 | 2027-11-30 | ✓ |  |  |  | Not started | Document sync complete | 7. Document Synchronisation
| 8. Status Synchronisation | 8.1 | Status model harmonisation | Business Analyst | 7.1 | 12 | 1 | 2027-10-01 | 2027-10-31 | ✓ | ✓ |  |  | Not started | Status model | 8. Status Synchronisation
|  | 8.2 | Status sync build (bi-directional) | Integration Engineer | 8.1 | 13 | 1 | 2027-11-01 | 2027-11-30 | ✓ | ✓ | ✓ |  | Not started | Status sync build | 8. Status Synchronisation
|  | 8.3 | Webhook / event triggers for status | Integration Engineer | 8.2 | 13 | 1 | 2027-11-01 | 2027-11-30 | ✓ |  |  |  | Not started | Event triggers | 8. Status Synchronisation
|  | 8.4 | Status sync testing (GATE) | QA Lead | 8.2,8.3 | 14 | 1 | 2027-12-01 | 2027-12-31 | ✓ |  |  |  | Not started | Status sync complete | 8. Status Synchronisation
| 9. Comments & To-Do Sync | 9.1 | Remarks / Comments API validation & mapping | Integration Engineer | 2.5 | 13 | 1 | 2027-11-01 | 2027-11-30 | ✓ |  | ✓ |  | Not started | Remarks mapping | 9. Comments & To-Do Sync
|  | 9.2 | Comments & review-notes sync build | Integration Engineer | 9.1 | 14 | 1 | 2027-12-01 | 2027-12-31 | ✓ |  |  |  | Not started | Comments sync build | 9. Comments & To-Do Sync
|  | 9.3 | To-do / assignments sync build | Integration Engineer | 9.1 | 14 | 1 | 2027-12-01 | 2027-12-31 | ✓ |  |  |  | Not started | To-do sync build | 9. Comments & To-Do Sync
|  | 9.4 | Comments & to-do testing (GATE) | QA Lead | 9.2,9.3 | 15 | 1 | 2028-01-01 | 2028-01-31 | ✓ |  |  |  | Not started | Comments & to-do complete | 9. Comments & To-Do Sync
| 10. Workflow Automation | 10.1 | Event-based automation-rules design | Solution Architect | 8.4 | 14 | 1 | 2027-12-01 | 2027-12-31 | ✓ | ✓ |  |  | Not started | Automation rules | 10. Workflow Automation
|  | 10.2 | Workflow orchestration build | Integration Engineer | 10.1 | 15 | 2 | 2028-01-01 | 2028-02-29 | ✓ |  |  |  | Not started | Orchestration build | 10. Workflow Automation
|  | 10.3 | Cross-platform workflow triggers | Integration Engineer | 10.2 | 16 | 1 | 2028-02-01 | 2028-02-29 | ✓ | ✓ | ✓ |  | Not started | Cross-platform triggers | 10. Workflow Automation
|  | 10.4 | Exception & escalation handling | Integration Engineer | 10.2 | 16 | 1 | 2028-02-01 | 2028-02-29 | ✓ |  |  |  | Not started | Exception handling | 10. Workflow Automation
|  | 10.5 | Workflow automation testing (GATE) | QA Lead | 10.3,10.4 | 17 | 1 | 2028-03-01 | 2028-03-31 | ✓ |  |  |  | Not started | Workflow automation complete | 10. Workflow Automation
| 11. Monitoring & Audit | 11.1 | Monitoring & observability dashboards | DevOps Engineer | 10.2 | 16 | 2 | 2028-02-01 | 2028-03-31 | ✓ |  |  |  | Not started | Dashboards | 11. Monitoring & Audit
|  | 11.2 | Audit trail & compliance logging | Security Lead | 11.1 | 17 | 2 | 2028-03-01 | 2028-04-30 | ✓ |  |  |  | Not started | Audit logging | 11. Monitoring & Audit
|  | 11.3 | Alerting & SLA reporting | DevOps Engineer | 11.1 | 18 | 1 | 2028-04-01 | 2028-04-30 | ✓ |  |  |  | Not started | Alerting & SLA | 11. Monitoring & Audit
|  | 11.4 | Data-privacy compliance review per country | Security Lead | 11.2 | 18 | 1 | 2028-04-01 | 2028-04-30 | ✓ |  |  | ✓ | Not started | Privacy sign-off | 11. Monitoring & Audit
|  | 11.5 | Monitoring & audit acceptance (GATE) | QA Lead | 11.3,11.4 | 19 | 1 | 2028-05-01 | 2028-05-31 | ✓ |  |  |  | Not started | Monitoring accepted | 11. Monitoring & Audit
4. UAT per region | 12. UAT per region | 12.1 | UAT strategy, scripts & entry / exit criteria | QA Lead | 10.5 | 17 | 1 | 2028-03-01 | 2028-03-31 | ✓ |  |  | ✓ | Not started | UAT pack | 12. UAT per region
|  | 12.2 | UAT — South Africa (Wave 1 pilot) | Country SME / QA Lead | 12.1,11.5 | 18 | 1 | 2028-04-01 | 2028-04-30 | ✓ |  |  | ✓ | Not started | SA UAT sign-off | 12. UAT per region
|  | 12.3 | UAT — Nigeria & Kenya (Wave 2) | Country SMEs | 13.2 | 20 | 1 | 2028-06-01 | 2028-06-30 | ✓ |  |  | ✓ | Not started | NG & KE UAT sign-off | 12. UAT per region
|  | 12.4 | UAT — Ghana, Tanzania & Uganda (Wave 3) | Country SMEs | 13.4 | 22 | 1 | 2028-08-01 | 2028-08-31 | ✓ |  |  | ✓ | Not started | GH, TZ & UG UAT sign-off | 12. UAT per region
5. Deployment per region | 13. Deployment & Rollout | 13.1 | Wave 1 go-live — South Africa | Country SME / PM | 12.2 | 19 | 1 | 2028-05-01 | 2028-05-31 | ✓ | ✓ |  | ✓ | Not started | SA in production | 13. Deployment & Rollout
|  | 13.2 | Wave 1 hypercare & stabilisation | Programme Manager | 13.1 | 19 | 1 | 2028-05-01 | 2028-05-31 | ✓ |  |  | ✓ | Not started | Wave 1 stabilised | 13. Deployment & Rollout
|  | 13.3 | Wave 2 go-live — Nigeria & Kenya | Country SMEs | 12.3 | 21 | 1 | 2028-07-01 | 2028-07-31 | ✓ | ✓ |  | ✓ | Not started | NG & KE in production | 13. Deployment & Rollout
|  | 13.4 | Wave 2 hypercare | Programme Manager | 13.3 | 21 | 1 | 2028-07-01 | 2028-07-31 | ✓ |  |  | ✓ | Not started | Wave 2 stabilised | 13. Deployment & Rollout
|  | 13.5 | Wave 3 go-live — Ghana, Tanzania & Uganda | Country SMEs | 12.4 | 23 | 1 | 2028-09-01 | 2028-09-30 | ✓ | ✓ |  | ✓ | Not started | GH, TZ & UG in production | 13. Deployment & Rollout
|  | 13.6 | Wave 3 hypercare | Programme Manager | 13.5 | 23 | 1 | 2028-09-01 | 2028-09-30 | ✓ |  |  | ✓ | Not started | Wave 3 stabilised | 13. Deployment & Rollout
|  | 13.7 | Programme close, benefits & handover to run | Programme Manager | 13.6 | 24 | 1 | 2028-10-01 | 2028-10-31 | ✓ | ✓ |  | ✓ | Not started | Programme closure | 13. Deployment & Rollout
How to use: update only the Status column as work progresses, and the Mo. / Dur. columns if a task moves. Start and end dates recalculate automatically. GATE tasks are phase exit points — they need steering-committee sign-off before the next phase starts.
Formulas:
Start date = EDATE(Charter!$D11,[Mo.]-1)
End date = EDATE(Charter!$D11,[Mo.]-1+[Dur.])-1

## Timeline
PROGRAMME TIMELINE · 24 MONTHS
Phase bars and milestone markers are generated from the Project Plan and Milestones tabs.
|  |  | YEAR 1 | [11 empty] | YEAR 2
|  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4
Phase | Start | Finish | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | 2027-11-01 | 2027-12-01 | 2028-01-01 | 2028-02-01 | 2028-03-01 | 2028-04-01 | 2028-05-01 | 2028-06-01 | 2028-07-01 | 2028-08-01 | 2028-09-01 | 2028-10-01
1. Africa Assessment | 2026-11-01 | 2027-01-31
2. Technical Discovery | 2026-12-01 | 2027-02-28
3. Documentation & Sign-off | 2027-02-01 | 2027-04-30
4. Foundation Integration Layer | 2027-02-01 | 2027-06-30
5. Client & Engagement Sync | 2027-04-01 | 2027-07-31
6. Trial Balance & GL Integration | 2027-06-01 | 2027-10-31
7. Document Synchronisation | 2027-08-01 | 2027-11-30
8. Status Synchronisation | 2027-10-01 | 2027-12-31
9. Comments & To-Do Sync | 2027-11-01 | 2028-01-31
10. Workflow Automation | 2027-12-01 | 2028-03-31
11. Monitoring & Audit | 2028-02-01 | 2028-05-31
12. UAT per region | 2028-03-01 | 2028-08-31
13. Deployment & Rollout | 2028-05-01 | 2028-10-31
◆ Milestones / gates |  |  |  |  | ◆ | ◆ |  | ◆ |  | ◆ | ◆ |  |  | ◆ | ◆ | ◆ | ◆ |  | ◆ |  | ◆ |  | ◆ |  | ◆ | ◆
Legend |  | Phase active
| ◆ | Milestone / gate month
Current month

## Milestones
MILESTONES & PHASE GATES
Target dates are calculated from the programme start date. A gate is a decision point with evidence, not a status update.
ID | Milestone | Phase | Month | Target date | Owner | Status | Acceptance criteria / evidence required
MS-01 | Assessment & prioritisation signed off | 1. Africa Assessment | M3 | 2027-01-31 | Programme Manager | Not started | Prioritised requirements and country scope approved by the steering committee
MS-02 | Architecture baseline approved | 2. Technical Discovery | M4 | 2027-02-28 | Solution Architect | Not started | Target architecture, security design and SyncAPI approach signed off
MS-03 | Stakeholder documentation signed off — all six countries | 3. Documentation & Sign-off | M6 | 2027-04-30 | Programme Manager | Not started | BRD, functional specification and privacy pack approved by tax, IT and vendors
MS-04 | Foundation layer ready | 4. Foundation Integration Layer | M8 | 2027-06-30 | Integration Lead | Not started | Agent, authentication, messaging and core connector pass integration test
MS-05 | Client & engagement sync complete | 5. Client & Engagement Sync | M9 | 2027-07-31 | QA Lead | Not started | Clients, users, engagements and periods synchronise reliably
MS-06 | TB / GL synchronisation validated | 6. Trial Balance & GL Integration | M12 | 2027-10-31 | Solution Architect | Not started | TB and GL sync end-to-end with reconciliation controls passing
MS-07 | Document sync complete | 7. Document Synchronisation | M13 | 2027-11-30 | QA Lead | Not started | Documents, schedules and packs synchronise with versioning
MS-08 | Status sync complete | 8. Status Synchronisation | M14 | 2027-12-31 | QA Lead | Not started | Bi-directional status updates verified
MS-09 | Comments & to-do sync complete | 9. Comments & To-Do Sync | M15 | 2028-01-31 | QA Lead | Not started | Comments, review notes, assignments and to-dos synchronise
MS-10 | Workflow automation complete | 10. Workflow Automation | M17 | 2028-03-31 | Solution Architect | Not started | Event-based automation with exception handling verified
MS-11 | Monitoring & audit accepted | 11. Monitoring & Audit | M19 | 2028-05-31 | QA Lead | Not started | Dashboards, audit trail, alerting and privacy review accepted
MS-12 | Wave 1 go-live — South Africa | 13. Deployment & Rollout | M19 | 2028-05-31 | Country SME / PM | Not started | SA pilot in production; hypercare exit criteria met
MS-13 | Wave 2 go-live — Nigeria & Kenya | 13. Deployment & Rollout | M21 | 2028-07-31 | Country SMEs | Not started | NG and KE in production; hypercare exit criteria met
MS-14 | Wave 3 go-live — Ghana, Tanzania & Uganda | 13. Deployment & Rollout | M23 | 2028-09-30 | Country SMEs | Not started | GH, TZ and UG in production; hypercare exit criteria met
MS-15 | Programme closure & handover to run | 13. Deployment & Rollout | M24 | 2028-10-31 | Programme Manager | Not started | Benefits realised, handover to run complete, programme closed

## Risks
RISK REGISTER
Likelihood × impact, each scored 1–5. Score 15+ high · 8–14 medium · below 8 low.
ID | Category | Risk | L | I | Score | Rating | Mitigation / response | Owner | Status
R-01 | Vendor / Access | SyncAPI access not granted or delayed by Silverfin, blocking TB / GL synchronisation | 5 | 5 | 25 | High | Raise a formal access request during discovery; secure a vendor SLA and escalation path; design a fallback TB import | Integration Lead | Open
R-02 | Technical | Comments / To-Do (Remarks) APIs unsupported or limited bi-directionally | 4 | 3 | 12 | Medium | Early validation spike in Technical Discovery; agree a one-way fallback design if constrained | Integration Engineer | Open
R-03 | Data | Trial-balance and chart-of-accounts mapping inconsistencies across the six countries | 4 | 4 | 16 | High | Account-mapping lists; transformation rules; reconciliation controls; per-country validation | Data Specialist | Open
R-04 | Compliance | Data residency and privacy differences (POPIA, NDPA, Kenya / TZ / UG / GH DPAs) | 3 | 5 | 15 | High | Data Protection Impact Assessment; regional hosting; per-jurisdiction legal review | Security Lead | Open
R-05 | Scope | Country-specific statutory and tax requirements expand scope | 4 | 3 | 12 | Medium | Change control; country prioritisation; MVP-first per market | Programme Manager | Open
R-06 | Resource | Scarcity of Silverfin / Intela integration skills | 4 | 4 | 16 | High | Early staffing; vendor enablement; structured knowledge transfer; reuse of the architecture | Programme Manager | Open
R-07 | Dependency | Intela Integration Agent maturity or feature limitations | 3 | 4 | 12 | Medium | Proof of concept; India CTR reference; vendor engagement on the roadmap | Integration Lead | Open
R-08 | Schedule | 24-month multi-country rollout slips against plan | 4 | 4 | 16 | High | Wave-based rollout; critical-path management; phase-gate buffers; hypercare windows | Programme Manager | Open
R-09 | Performance | API rate limits or performance degradation at scale | 3 | 3 | 9 | Medium | Batching and throttling; caching; load and volume testing before go-live | Solution Architect | Open
R-10 | Change | Low practitioner adoption across countries | 3 | 4 | 12 | Medium | Change management; training; country champions; phased cut-over | Change / Training Lead | Open
R-11 | Security | Credential and secret sprawl across environments and countries | 3 | 4 | 12 | Medium | Central vault; rotation; least privilege; secrets scanning in CI/CD | Security Lead | Open
R-12 | Quality | Bi-directional sync conflicts — source-of-truth ambiguity | 4 | 4 | 16 | High | Define the system of record per data domain up front (see open question Q-01) | Solution Architect | Open
R-13 | Vendor | Silverfin or Intela roadmap changes mid-programme | 2 | 3 | 6 | Low | Vendor governance; versioned APIs; contract change control | Programme Manager | Open
R-14 | Financial | Budget overrun on per-country customisation | 3 | 4 | 12 | Medium | Reusable architecture; standardisation; stage-gated funding | Programme Manager | Open
R-15 | Operational | Silent integration failures without monitoring | 3 | 4 | 12 | Medium | Observability, alerting and audit trail delivered in phase 11 | DevOps Engineer | Open
SCORING GUIDE
1 – 7 |  | Low | Accept and monitor at the fortnightly review.
8 – 14 |  | Medium | Named owner and a dated response; reviewed monthly.
15 – 25 |  | High | Escalate to the sponsor within 48 hours; reviewed at every checkpoint.

## Dependencies
DEPENDENCIES, ASSUMPTIONS & OPEN QUESTIONS
What the programme relies on but does not control, and what must be resolved during discovery.
ID | Type | Dependency | Description | Needed by | Owner | Status
D-01 | Vendor | Silverfin SyncAPI access | Access to SyncAPI to synchronise trial balance and general ledger — the critical-path dependency | Phase 6 (by M8) | Integration Lead | Open
D-02 | Vendor | Intela Integration Agent | Availability and configuration of the strategic integration mechanism | Phase 4 (by M4) | Integration Lead | Open
D-03 | Internal | India CTR reference | Access to India CTR documentation and team for the reference architecture | Phase 2 (by M3) | Solution Architect | Open
D-04 | Vendor | Silverfin API credentials | API credentials per country / firm environment | Phase 4 (by M5) | Security Lead | Open
D-05 | Internal | Country SME availability | Part-time tax SMEs for all six countries throughout the programme | Phase 1 onward | Country Leads | Open
D-06 | Internal | Cloud tenancy & environments | Provisioning of dev / test / UAT / prod meeting data-residency needs | Phase 4 (by M4) | DevOps Engineer | Open
D-07 | Internal | Data-privacy sign-off | Per-jurisdiction privacy approval (POPIA, NDPA and others) | Phase 3 & 11 | Security Lead | Open
D-08 | Internal | Client CoA & mapping data | Charts of accounts and mapping source data per client | Phase 5–6 (by M7) | Data Specialist | Open
D-09 | Vendor | Silverfin licensing | Confirmed Silverfin licensing for each country in scope | Phase 1 (by M3) | Programme Manager | Open
D-10 | Internal | Change & training resource | Change-management and training capacity for rollout | Rollout (M18+) | Change / Training Lead | Open
PLANNING ASSUMPTIONS
ID | Assumption |  |  | Impact if invalid | Owner | Status
A-01 | Silverfin SyncAPI is available under Deloitte licensing and access will be granted |  |  | Blocks TB / GL sync; re-plan phase 6 | Integration Lead | To confirm
A-02 | The Intela Integration Agent is the strategic integration mechanism |  |  | Architecture rework | Solution Architect | To confirm
A-03 | The India CTR integration is available as a reference pattern |  |  | Slower discovery; more design effort | Solution Architect | To confirm
A-04 | Cloud tenancy can meet each country's data-residency needs |  |  | Hosting redesign; compliance risk | Security Lead | To confirm
A-05 | Country SMEs are available part-time throughout the programme |  |  | Requirements and rollout delays | Programme Manager | To confirm
A-06 | Bi-directional sync is required and the system of record is confirmed per data domain |  |  | Sync conflicts (see R-12) | Solution Architect | To confirm
A-07 | Budget and resourcing are approved for a 24-month programme |  |  | Scope or timeline reduction | Sponsor | To confirm
OPEN QUESTIONS — to resolve in discovery
ID | Question |  |  | Why it matters | Owner | Status
Q-01 | Source of truth — which platform is the system of record for each data domain? |  |  | Determines bi-directional sync design and conflict rules | Solution Architect | Open
Q-02 | SyncAPI access — how is it provisioned; what are the timelines, cost and per-country implications? |  |  | Critical-path dependency for TB / GL | Integration Lead | Open
Q-03 | Comments API — are Remarks / Comments and to-do fully supported bi-directionally? |  |  | Confirms phase 9 scope and fallback | Integration Engineer | Open
Q-04 | TB import APIs — confirmed endpoints, formats and volume limits? |  |  | Drives TB integration design and performance | Data Specialist | Open
Q-05 | Country-specific requirements — statutory and tax differences affecting mapping? |  |  | Scope, mapping and rollout sequencing | Country SMEs | Open
Q-06 | Rollout priorities — confirm country sequencing and the South Africa pilot? |  |  | Locks the wave plan and schedule | Programme Manager | Open

## Country Rollout
COUNTRY ASSESSMENT & ROLLOUT WAVES
Readiness across the six markets and the wave sequencing that follows from it.
Country | Practice maturity | Silverfin adoption | Data-privacy regime | Complexity | Wave | Priority | Notes
South Africa | High | High | POPIA | Medium | Wave 1 | Pilot | Largest Deloitte Africa tax practice; strongest Silverfin base; closest to the target operating model
Nigeria | High | Medium | NDPA / NDPR | High | Wave 2 | High | Strong local team; active Nigeria Tax Act 2025 work; high statutory complexity
Kenya | Medium | Medium | Kenya DPA 2019 | Medium | Wave 2 | High | East-Africa hub; regional coordination point
Ghana | Medium | Low | DPA 2012 | Medium | Wave 3 | Medium | West-Africa rollout; requires enablement uplift
Tanzania | Low | Low | PDPA 2022 | Medium | Wave 3 | Medium | Lower current adoption; standardise on the established pattern
Uganda | Low | Low | DPPA 2019 | Medium | Wave 3 | Medium | Lower current adoption; leverage East-Africa learnings
ROLLOUT WAVES
Wave | Countries | Months | Scope |  |  | Entry criteria | Exit / go-live criteria
Wave 0 | Build & pilot preparation (all countries) | M1–M17 | Foundation layer plus all integration modules (client, TB / GL, documents, status, comments, workflow, monitoring) |  |  | Charter approved; SyncAPI access and architecture baseline confirmed | All modules pass integration testing; UAT scripts ready
Wave 1 | South Africa (pilot) | M18–M19 | Full solution pilot in the most mature market |  |  | Wave 0 complete; monitoring and audit accepted; SA environment ready | SA in production; reconciliation clean; hypercare exit met
Wave 2 | Nigeria, Kenya | M20–M21 | Country configuration, UAT and go-live for NG and KE |  |  | Wave 1 stabilised; country requirements and mappings confirmed | NG and KE in production; hypercare exit met
Wave 3 | Ghana, Tanzania, Uganda | M22–M24 | Country configuration, UAT and go-live for GH, TZ and UG; programme closure |  |  | Wave 2 stabilised; enablement and training complete | All six countries live; benefits realised; handover to run