## Charter
INTELA – SILVERFIN INTEGRATION · 24-MONTH PROGRAMME MANAGEMENT PLAN
Deloitte Africa ¦ Tax Technology · South Africa · Nigeria · Ghana · Kenya · Tanzania · Uganda · CONFIDENTIAL — internal planning document
PROGRAMME CONTROL
Programme |  | Deloitte Africa — Intela–Silverfin Integration Programme
Sponsor |  | Deloitte Africa Tax & Legal Technology Leadership (to confirm)
Programme Manager |  | To be appointed
Prepared by |  | Tochukwu (El Tee) Owunwanne — Tax Technology, Deloitte Nigeria
PMO contact |  | Sharon Norambuena — Senior Manager: Africa Tax & Legal, Intela PMO
Programme start date |  | 2026-11-01
Programme end date |  | 2028-10-31
Desired deployment date |  | As soon as the integration is approved for use — aligned to each country's Intela deployment plan
Busy season constraint |  | Not applicable
Version / date |  | v2.0 · September 2026
◄ The yellow cell above is the only date you edit. Every start date, finish date, month column and milestone date in this workbook is calculated from it.
PROGRAMME CHARTER
Background |  | Tax practitioners across Deloitte Africa currently move documents, status updates and trial balances between Intela and Silverfin manually, running duplicate workflows with no unified view. This programme establishes a two-way integration so that data captured in Intela flows to Silverfin and back, removing manual effort and creating a single, reliable engagement view.
Objectives |  | 1. Deliver bi-directional trial balance and general ledger synchronisation via the Silverfin SyncAPI. 2. Synchronise documents, engagement status, comments and to-do items between the two platforms. 3. Automate event-based workflows and provide end-to-end monitoring and audit. 4. Roll the solution out across six African countries on a controlled, wave-based schedule.
Scope — in |  | Client and engagement sync · Trial balance and GL sync · Document sync · Status sync · Comments and to-do sync · Workflow automation · Monitoring and audit · Multi-country configuration and rollout across six countries.
Scope — out |  | Changes to core Intela or Silverfin product code · Migration of historical archives beyond an agreed cut-off · New tax-computation logic (delivered separately) · Countries outside the six named markets.
Delivery approach |  | Five stages, applied per region: (1) assessment of tools and build, (2) document sign-off from all stakeholders, (3) architectural build, (4) UAT, (5) deployment. Build runs M1–M19 centrally; UAT and deployment run per region in three waves from M18.
Success criteria |  | Zero manual TB uploads for onboarded engagements · Documents and status reconcile automatically within SLA · A single unified engagement view for practitioners · Successful go-live in all six countries with hypercare exit met.
Indicative effort |  | MVP 12–16 weeks · enterprise build 6–9 months · full multi-country programme up to 24 months. Budget to be confirmed after technical discovery and SyncAPI licensing clarification.
Governance |  | Programme Director / Sponsor · Programme Manager · Solution Architect · Integration Lead · Country SMEs (×6) · Security & Compliance Lead · QA Lead · Change / Training Lead. The steering committee reviews at each phase gate.
Constraints & assumptions |  | Dependent on Silverfin SyncAPI access and the Intela Integration Agent (see the Dependencies tab). Country SMEs available part-time throughout. Data residency and privacy addressed per jurisdiction.
PROGRAMME STATUS — calculated from the Project Plan, Milestones and Risks tabs
Tasks in plan | Completed | In progress | Not started | At risk / on hold | Milestones met | High risks open
70 | 0 | 0 | 70 | 0 | 0 | 6
Added in this version: a dedicated 'Documentation & sign-off' phase (3.1–3.5) and a separate UAT phase per region (12.1–12.4), so the workbook follows the agreed five-step regional approach. Deployment is now its own phase (13.1–13.7).

## Project Plan
PROJECT MANAGEMENT PLAN · INTELA – SILVERFIN INTEGRATION
Milestone → phase → sub-scope. Dates are calculated from the programme start date on the Charter tab.
RESPONSIBILITY
Milestone | Project phase | WBS | Sub-scope / task | Owner (role) | Dependencies | Mo. | Dur. | Start date | End date | Deloitte Tax Technology | Intela PMO / Product | Silverfin (vendor) | Country practice / SMEs | Status | Key deliverable / comments | Phase key (helper — do not delete)
1. Assessment of tools / build per region | 1. Africa Assessment | 1.1 | Programme mobilisation & governance set-up | Programme Manager | — | 1 | 1 | 2026-11-01 | 2026-11-30 | ✓ | ✓ |  |  | Not started | Governance model & charter | 1. Africa Assessment
|  | 1.2 | Stakeholder mapping across the six countries | Business Analyst | 1.1 | 1 | 1 | 2026-11-01 | 2026-11-30 | ✓ |  |  | ✓ | Not started | Stakeholder register | 1. Africa Assessment
|  | 1.3 | Current-state (as-is) process assessment | Business Analyst | 1.1 | 1 | 2 | 2026-11-01 | 2026-12-31 | ✓ |  |  | ✓ | Not started | As-is process maps | 1. Africa Assessment
|  | 1.4 | Country tax-compliance requirements catalogue | Country SMEs | 1.2 | 2 | 2 | 2026-12-01 | 2027-01-31 | ✓ |  |  | ✓ | Not started | Requirements catalogue | 1. Africa Assessment
|  | 1.5 | Silverfin footprint & licensing assessment per region | Solution Architect | 1.3 | 2 | 1 | 2026-12-01 | 2026-12-31 | ✓ |  | ✓ |  | Not started | Footprint & licensing report | 1. Africa Assessment
|  | 1.6 | Assessment report & prioritisation (GATE) | Programme Manager | 1.4,1.5 | 3 | 1 | 2027-01-01 | 2027-01-31 | ✓ | ✓ |  | ✓ | Not started | Assessment sign-off | 1. Africa Assessment
| 2. Technical Discovery | 2.1 | Silverfin API capability review | Solution Architect | 1.5 | 2 | 2 | 2026-12-01 | 2027-01-31 | ✓ |  | ✓ |  | Not started | API capability matrix | 2. Technical Discovery
|  | 2.2 | SyncAPI access request & validation (TB / GL) | Integration Lead | 1.1 | 2 | 2 | 2026-12-01 | 2027-01-31 | ✓ |  | ✓ |  | Not started | SyncAPI access confirmed | 2. Technical Discovery
|  | 2.3 | Intela Integration Agent assessment | Integration Lead | 2.1 | 3 | 1 | 2027-01-01 | 2027-01-31 | ✓ | ✓ |  |  | Not started | Agent assessment note | 2. Technical Discovery
|  | 2.4 | India CTR reference-architecture review | Solution Architect | 2.1 | 3 | 1 | 2027-01-01 | 2027-01-31 | ✓ | ✓ |  |  | Not started | Reference-pattern report | 2. Technical Discovery
|  | 2.5 | TB / Comments / To-Do API validation spike | Integration Engineer | 2.1 | 3 | 2 | 2027-01-01 | 2027-02-28 | ✓ |  | ✓ |  | Not started | Validation findings | 2. Technical Discovery
|  | 2.6 | Target architecture & security design (GATE) | Solution Architect | 2.2,2.3,2.5 | 4 | 1 | 2027-02-01 | 2027-02-28 | ✓ | ✓ |  |  | Not started | Architecture baseline | 2. Technical Discovery
2. Document sign-off from all stakeholders | 3. Documentation & Sign-off | 3.1 | Business requirements document per region | Business Analyst | 1.6,2.6 | 4 | 2 | 2027-02-01 | 2027-03-31 | ✓ |  |  | ✓ | Not started | BRD per country | 3. Documentation & Sign-off
|  | 3.2 | Functional & technical specification (solution design) | Solution Architect | 2.6 | 5 | 2 | 2027-03-01 | 2027-04-30 | ✓ | ✓ |  |  | Not started | FSD / solution design document | 3. Documentation & Sign-off
|  | 3.3 | Data-privacy & residency assessment pack (POPIA, NDPA, DPAs) | Security Lead | 3.1 | 5 | 1 | 2027-03-01 | 2027-03-31 | ✓ |  |  | ✓ | Not started | DPIA pack per jurisdiction | 3. Documentation & Sign-off
|  | 3.4 | Integration approval & security review (Intela & Silverfin) | Integration Lead | 3.2 | 6 | 1 | 2027-04-01 | 2027-04-30 | ✓ | ✓ | ✓ |  | Not started | Vendor integration approval | 3. Documentation & Sign-off
|  | 3.5 | Stakeholder document sign-off — all six countries (GATE) | Programme Manager | 3.3,3.4 | 6 | 1 | 2027-04-01 | 2027-04-30 | ✓ | ✓ |  | ✓ | Not started | Signed-off documentation set | 3. Documentation & Sign-off
3. Architectural build per region | 4. Foundation Integration Layer | 4.1 | Environment provisioning (dev / test / UAT / prod) | DevOps Engineer | 2.6 | 4 | 1 | 2027-02-01 | 2027-02-28 | ✓ |  |  |  | Not started | Environments live | 4. Foundation Integration Layer
|  | 4.2 | Integration Agent deployment & configuration | Integration Lead | 2.6 | 4 | 2 | 2027-02-01 | 2027-03-31 | ✓ | ✓ |  |  | Not started | Agent deployed | 4. Foundation Integration Layer
|  | 4.3 | Authentication, authorisation & secrets management | Security Lead | 4.1 | 5 | 2 | 2027-03-01 | 2027-04-30 | ✓ | ✓ |  |  | Not started | Auth & vault ready | 4. Foundation Integration Layer
|  | 4.4 | Event bus / messaging framework | Integration Engineer | 4.1 | 5 | 2 | 2027-03-01 | 2027-04-30 | ✓ |  |  |  | Not started | Messaging framework | 4. Foundation Integration Layer
|  | 4.5 | Core Silverfin connector (companies / periods / users) | Integration Engineer | 4.3,4.4 | 6 | 2 | 2027-04-01 | 2027-05-31 | ✓ |  | ✓ |  | Not started | Connector v1 | 4. Foundation Integration Layer
|  | 4.6 | Error handling, retry & logging framework | Integration Engineer | 4.5 | 7 | 1 | 2027-05-01 | 2027-05-31 | ✓ |  |  |  | Not started | Resilience framework | 4. Foundation Integration Layer
|  | 4.7 | CI/CD pipeline & infrastructure-as-code | DevOps Engineer | 4.1 | 6 | 2 | 2027-04-01 | 2027-05-31 | ✓ |  |  |  | Not started | CI/CD pipeline | 4. Foundation Integration Layer
|  | 4.8 | Foundation layer integration test (GATE) | QA Lead | 4.5,4.7 | 8 | 1 | 2027-06-01 | 2027-06-30 | ✓ |  |  |  | Not started | Foundation layer ready | 4. Foundation Integration Layer
| 5. Client & Engagement Sync | 5.1 | Client / entity data-model mapping | Data Specialist | 4.5 | 6 | 2 | 2027-04-01 | 2027-05-31 | ✓ |  | ✓ |  | Not started | Mapping specification | 5. Client & Engagement Sync
|  | 5.2 | Client mapping & account-mapping lists | Data Specialist | 5.1 | 7 | 2 | 2027-05-01 | 2027-06-30 | ✓ |  |  | ✓ | Not started | Mapping lists | 5. Client & Engagement Sync
|  | 5.3 | User synchronisation | Integration Engineer | 4.5 | 7 | 1 | 2027-05-01 | 2027-05-31 | ✓ | ✓ |  |  | Not started | User sync build | 5. Client & Engagement Sync
|  | 5.4 | Engagement / period linkage | Integration Engineer | 5.2 | 8 | 1 | 2027-06-01 | 2027-06-30 | ✓ | ✓ |  |  | Not started | Period linkage | 5. Client & Engagement Sync
|  | 5.5 | Client & engagement sync testing (GATE) | QA Lead | 5.3,5.4 | 9 | 1 | 2027-07-01 | 2027-07-31 | ✓ |  |  |  | Not started | Client sync complete | 5. Client & Engagement Sync
| 6. Trial Balance & GL Integration | 6.1 | SyncAPI integration design (TB & GL) | Solution Architect | 2.2,4.8 | 8 | 1 | 2027-06-01 | 2027-06-30 | ✓ |  | ✓ |  | Not started | TB / GL design | 6. Trial Balance & GL Integration
|  | 6.2 | TB import mapping & transformation rules | Data Specialist | 5.2 | 8 | 2 | 2027-06-01 | 2027-07-31 | ✓ |  |  | ✓ | Not started | Transformation rules | 6. Trial Balance & GL Integration
|  | 6.3 | General Ledger synchronisation build | Integration Engineer | 6.1 | 9 | 2 | 2027-07-01 | 2027-08-31 | ✓ |  | ✓ |  | Not started | GL sync build | 6. Trial Balance & GL Integration
|  | 6.4 | TB push Intela → Silverfin build | Integration Engineer | 6.2,6.3 | 10 | 2 | 2027-08-01 | 2027-09-30 | ✓ | ✓ | ✓ |  | Not started | TB sync build | 6. Trial Balance & GL Integration
|  | 6.5 | Account-mapping validation & reconciliation | Data Specialist | 6.4 | 11 | 1 | 2027-09-01 | 2027-09-30 | ✓ |  |  | ✓ | Not started | Reconciliation controls | 6. Trial Balance & GL Integration
|  | 6.6 | TB / GL end-to-end testing (GATE) | QA Lead | 6.4,6.5 | 12 | 1 | 2027-10-01 | 2027-10-31 | ✓ |  |  |  | Not started | TB / GL validated | 6. Trial Balance & GL Integration
| 7. Document Synchronisation | 7.1 | Document taxonomy & metadata mapping | Business Analyst | 5.5 | 10 | 1 | 2027-08-01 | 2027-08-31 | ✓ |  |  | ✓ | Not started | Document taxonomy | 7. Document Synchronisation
|  | 7.2 | Document sync build (documents, schedules, packs) | Integration Engineer | 7.1 | 11 | 2 | 2027-09-01 | 2027-10-31 | ✓ | ✓ |  |  | Not started | Document sync build | 7. Document Synchronisation
|  | 7.3 | Live Export Documents integration | Integration Engineer | 7.2 | 12 | 1 | 2027-10-01 | 2027-10-31 | ✓ |  | ✓ |  | Not started | Live export integrated | 7. Document Synchronisation
|  | 7.4 | Document versioning & retention rules | Security Lead | 7.2 | 12 | 1 | 2027-10-01 | 2027-10-31 | ✓ |  |  |  | Not started | Versioning rules | 7. Document Synchronisation
|  | 7.5 | Document sync testing (GATE) | QA Lead | 7.3,7.4 | 13 | 1 | 2027-11-01 | 2027-11-30 | ✓ |  |  |  | Not started | Document sync complete | 7. Document Synchronisation
| 8. Status Synchronisation | 8.1 | Status model harmonisation | Business Analyst | 7.1 | 12 | 1 | 2027-10-01 | 2027-10-31 | ✓ | ✓ |  |  | Not started | Status model | 8. Status Synchronisation
|  | 8.2 | Status sync build (bi-directional) | Integration Engineer | 8.1 | 13 | 1 | 2027-11-01 | 2027-11-30 | ✓ | ✓ | ✓ |  | Not started | Status sync build | 8. Status Synchronisation
|  | 8.3 | Webhook / event triggers for status | Integration Engineer | 8.2 | 13 | 1 | 2027-11-01 | 2027-11-30 | ✓ |  |  |  | Not started | Event triggers | 8. Status Synchronisation
|  | 8.4 | Status sync testing (GATE) | QA Lead | 8.2,8.3 | 14 | 1 | 2027-12-01 | 2027-12-31 | ✓ |  |  |  | Not started | Status sync complete | 8. Status Synchronisation
| 9. Comments & To-Do Sync | 9.1 | Remarks / Comments API validation & mapping | Integration Engineer | 2.5 | 13 | 1 | 2027-11-01 | 2027-11-30 | ✓ |  | ✓ |  | Not started | Remarks mapping | 9. Comments & To-Do Sync
|  | 9.2 | Comments & review-notes sync build | Integration Engineer | 9.1 | 14 | 1 | 2027-12-01 | 2027-12-31 | ✓ |  |  |  | Not started | Comments sync build | 9. Comments & To-Do Sync
|  | 9.3 | To-do / assignments sync build | Integration Engineer | 9.1 | 14 | 1 | 2027-12-01 | 2027-12-31 | ✓ |  |  |  | Not started | To-do sync build | 9. Comments & To-Do Sync
|  | 9.4 | Comments & to-do testing (GATE) | QA Lead | 9.2,9.3 | 15 | 1 | 2028-01-01 | 2028-01-31 | ✓ |  |  |  | Not started | Comments & to-do complete | 9. Comments & To-Do Sync
| 10. Workflow Automation | 10.1 | Event-based automation-rules design | Solution Architect | 8.4 | 14 | 1 | 2027-12-01 | 2027-12-31 | ✓ | ✓ |  |  | Not started | Automation rules | 10. Workflow Automation
|  | 10.2 | Workflow orchestration build | Integration Engineer | 10.1 | 15 | 2 | 2028-01-01 | 2028-02-29 | ✓ |  |  |  | Not started | Orchestration build | 10. Workflow Automation
|  | 10.3 | Cross-platform workflow triggers | Integration Engineer | 10.2 | 16 | 1 | 2028-02-01 | 2028-02-29 | ✓ | ✓ | ✓ |  | Not started | Cross-platform triggers | 10. Workflow Automation
|  | 10.4 | Exception & escalation handling | Integration Engineer | 10.2 | 16 | 1 | 2028-02-01 | 2028-02-29 | ✓ |  |  |  | Not started | Exception handling | 10. Workflow Automation
|  | 10.5 | Workflow automation testing (GATE) | QA Lead | 10.3,10.4 | 17 | 1 | 2028-03-01 | 2028-03-31 | ✓ |  |  |  | Not started | Workflow automation complete | 10. Workflow Automation
| 11. Monitoring & Audit | 11.1 | Monitoring & observability dashboards | DevOps Engineer | 10.2 | 16 | 2 | 2028-02-01 | 2028-03-31 | ✓ |  |  |  | Not started | Dashboards | 11. Monitoring & Audit
|  | 11.2 | Audit trail & compliance logging | Security Lead | 11.1 | 17 | 2 | 2028-03-01 | 2028-04-30 | ✓ |  |  |  | Not started | Audit logging | 11. Monitoring & Audit
|  | 11.3 | Alerting & SLA reporting | DevOps Engineer | 11.1 | 18 | 1 | 2028-04-01 | 2028-04-30 | ✓ |  |  |  | Not started | Alerting & SLA | 11. Monitoring & Audit
|  | 11.4 | Data-privacy compliance review per country | Security Lead | 11.2 | 18 | 1 | 2028-04-01 | 2028-04-30 | ✓ |  |  | ✓ | Not started | Privacy sign-off | 11. Monitoring & Audit
|  | 11.5 | Monitoring & audit acceptance (GATE) | QA Lead | 11.3,11.4 | 19 | 1 | 2028-05-01 | 2028-05-31 | ✓ |  |  |  | Not started | Monitoring accepted | 11. Monitoring & Audit
4. UAT per region | 12. UAT per region | 12.1 | UAT strategy, scripts & entry / exit criteria | QA Lead | 10.5 | 17 | 1 | 2028-03-01 | 2028-03-31 | ✓ |  |  | ✓ | Not started | UAT pack | 12. UAT per region
|  | 12.2 | UAT — South Africa (Wave 1 pilot) | Country SME / QA Lead | 12.1,11.5 | 18 | 1 | 2028-04-01 | 2028-04-30 | ✓ |  |  | ✓ | Not started | SA UAT sign-off | 12. UAT per region
|  | 12.3 | UAT — Nigeria & Kenya (Wave 2) | Country SMEs | 13.2 | 20 | 1 | 2028-06-01 | 2028-06-30 | ✓ |  |  | ✓ | Not started | NG & KE UAT sign-off | 12. UAT per region
|  | 12.4 | UAT — Ghana, Tanzania & Uganda (Wave 3) | Country SMEs | 13.4 | 22 | 1 | 2028-08-01 | 2028-08-31 | ✓ |  |  | ✓ | Not started | GH, TZ & UG UAT sign-off | 12. UAT per region
5. Deployment per region | 13. Deployment & Rollout | 13.1 | Wave 1 go-live — South Africa | Country SME / PM | 12.2 | 19 | 1 | 2028-05-01 | 2028-05-31 | ✓ | ✓ |  | ✓ | Not started | SA in production | 13. Deployment & Rollout
|  | 13.2 | Wave 1 hypercare & stabilisation | Programme Manager | 13.1 | 19 | 1 | 2028-05-01 | 2028-05-31 | ✓ |  |  | ✓ | Not started | Wave 1 stabilised | 13. Deployment & Rollout
|  | 13.3 | Wave 2 go-live — Nigeria & Kenya | Country SMEs | 12.3 | 21 | 1 | 2028-07-01 | 2028-07-31 | ✓ | ✓ |  | ✓ | Not started | NG & KE in production | 13. Deployment & Rollout
|  | 13.4 | Wave 2 hypercare | Programme Manager | 13.3 | 21 | 1 | 2028-07-01 | 2028-07-31 | ✓ |  |  | ✓ | Not started | Wave 2 stabilised | 13. Deployment & Rollout
|  | 13.5 | Wave 3 go-live — Ghana, Tanzania & Uganda | Country SMEs | 12.4 | 23 | 1 | 2028-09-01 | 2028-09-30 | ✓ | ✓ |  | ✓ | Not started | GH, TZ & UG in production | 13. Deployment & Rollout
|  | 13.6 | Wave 3 hypercare | Programme Manager | 13.5 | 23 | 1 | 2028-09-01 | 2028-09-30 | ✓ |  |  | ✓ | Not started | Wave 3 stabilised | 13. Deployment & Rollout
|  | 13.7 | Programme close, benefits & handover to run | Programme Manager | 13.6 | 24 | 1 | 2028-10-01 | 2028-10-31 | ✓ | ✓ |  | ✓ | Not started | Programme closure | 13. Deployment & Rollout
How to use: update only the Status column as work progresses, and the Mo. / Dur. columns if a task moves. Start and end dates recalculate automatically. GATE tasks are phase exit points — they need steering-committee sign-off before the next phase starts.
Formulas:
Start date = EDATE(Charter!$D11,[Mo.]-1)
End date = EDATE(Charter!$D11,[Mo.]-1+[Dur.])-1

## Timeline
PROGRAMME TIMELINE · 24 MONTHS
Phase bars and milestone markers are generated from the Project Plan and Milestones tabs.
|  |  | YEAR 1 | [11 empty] | YEAR 2
|  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4
Phase | Start | Finish | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | 2027-11-01 | 2027-12-01 | 2028-01-01 | 2028-02-01 | 2028-03-01 | 2028-04-01 | 2028-05-01 | 2028-06-01 | 2028-07-01 | 2028-08-01 | 2028-09-01 | 2028-10-01
1. Africa Assessment | 2026-11-01 | 2027-01-31
2. Technical Discovery | 2026-12-01 | 2027-02-28
3. Documentation & Sign-off | 2027-02-01 | 2027-04-30
4. Foundation Integration Layer | 2027-02-01 | 2027-06-30
5. Client & Engagement Sync | 2027-04-01 | 2027-07-31
6. Trial Balance & GL Integration | 2027-06-01 | 2027-10-31
7. Document Synchronisation | 2027-08-01 | 2027-11-30
8. Status Synchronisation | 2027-10-01 | 2027-12-31
9. Comments & To-Do Sync | 2027-11-01 | 2028-01-31
10. Workflow Automation | 2027-12-01 | 2028-03-31
11. Monitoring & Audit | 2028-02-01 | 2028-05-31
12. UAT per region | 2028-03-01 | 2028-08-31
13. Deployment & Rollout | 2028-05-01 | 2028-10-31
◆ Milestones / gates |  |  |  |  | ◆ | ◆ |  | ◆ |  | ◆ | ◆ |  |  | ◆ | ◆ | ◆ | ◆ |  | ◆ |  | ◆ |  | ◆ |  | ◆ | ◆
Legend |  | Phase active
| ◆ | Milestone / gate month
Current month

## Milestones
MILESTONES & PHASE GATES
Target dates are calculated from the programme start date. A gate is a decision point with evidence, not a status update.
ID | Milestone | Phase | Month | Target date | Owner | Status | Acceptance criteria / evidence required
MS-01 | Assessment & prioritisation signed off | 1. Africa Assessment | M3 | 2027-01-31 | Programme Manager | Not started | Prioritised requirements and country scope approved by the steering committee
MS-02 | Architecture baseline approved | 2. Technical Discovery | M4 | 2027-02-28 | Solution Architect | Not started | Target architecture, security design and SyncAPI approach signed off
MS-03 | Stakeholder documentation signed off — all six countries | 3. Documentation & Sign-off | M6 | 2027-04-30 | Programme Manager | Not started | BRD, functional specification and privacy pack approved by tax, IT and vendors
MS-04 | Foundation layer ready | 4. Foundation Integration Layer | M8 | 2027-06-30 | Integration Lead | Not started | Agent, authentication, messaging and core connector pass integration test
MS-05 | Client & engagement sync complete | 5. Client & Engagement Sync | M9 | 2027-07-31 | QA Lead | Not started | Clients, users, engagements and periods synchronise reliably
MS-06 | TB / GL synchronisation validated | 6. Trial Balance & GL Integration | M12 | 2027-10-31 | Solution Architect | Not started | TB and GL sync end-to-end with reconciliation controls passing
MS-07 | Document sync complete | 7. Document Synchronisation | M13 | 2027-11-30 | QA Lead | Not started | Documents, schedules and packs synchronise with versioning
MS-08 | Status sync complete | 8. Status Synchronisation | M14 | 2027-12-31 | QA Lead | Not started | Bi-directional status updates verified
MS-09 | Comments & to-do sync complete | 9. Comments & To-Do Sync | M15 | 2028-01-31 | QA Lead | Not started | Comments, review notes, assignments and to-dos synchronise
MS-10 | Workflow automation complete | 10. Workflow Automation | M17 | 2028-03-31 | Solution Architect | Not started | Event-based automation with exception handling verified
MS-11 | Monitoring & audit accepted | 11. Monitoring & Audit | M19 | 2028-05-31 | QA Lead | Not started | Dashboards, audit trail, alerting and privacy review accepted
MS-12 | Wave 1 go-live — South Africa | 13. Deployment & Rollout | M19 | 2028-05-31 | Country SME / PM | Not started | SA pilot in production; hypercare exit criteria met
MS-13 | Wave 2 go-live — Nigeria & Kenya | 13. Deployment & Rollout | M21 | 2028-07-31 | Country SMEs | Not started | NG and KE in production; hypercare exit criteria met
MS-14 | Wave 3 go-live — Ghana, Tanzania & Uganda | 13. Deployment & Rollout | M23 | 2028-09-30 | Country SMEs | Not started | GH, TZ and UG in production; hypercare exit criteria met
MS-15 | Programme closure & handover to run | 13. Deployment & Rollout | M24 | 2028-10-31 | Programme Manager | Not started | Benefits realised, handover to run complete, programme closed

## Document Sign-off
DOCUMENT SIGN-OFF REGISTER
Step 2 of the regional approach — every document that must be signed off, by whom, and where it stands.
COUNTRY SIGN-OFF
ID | Document | WBS | Author / owner | Version | Circulated | Review due | SA | NG | KE | GH | TZ | UG | Intela PMO | Silverfin | Overall status | Date signed off | Comments
DOC-01 | Programme charter & governance model | 1.1 | Programme Manager | v0.1 |  | 2026-11-30 | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Not started
DOC-02 | Stakeholder register — six countries | 1.2 | Business Analyst | v0.1 |  | 2026-11-30 | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Not started
DOC-03 | Current-state (as-is) process maps | 1.3 | Business Analyst | v0.1 |  | 2026-12-31 | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Not started
DOC-04 | Country tax-compliance requirements catalogue | 1.4 | Country SMEs | v0.1 |  | 2027-01-31 | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Not started
DOC-05 | Silverfin footprint & licensing report | 1.5 | Solution Architect | v0.1 |  | 2026-12-31 | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Not started
DOC-06 | Assessment report & prioritisation (Gate 1) | 1.6 | Programme Manager | v0.1 |  | 2027-01-31 | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Not started
DOC-07 | Silverfin API capability matrix | 2.1 | Solution Architect | v0.1 |  | 2027-01-31 | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Not started
DOC-08 | SyncAPI access confirmation & terms of use | 2.2 | Integration Lead | v0.1 |  | 2027-01-31 | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Not started
DOC-09 | Intela Integration Agent assessment note | 2.3 | Integration Lead | v0.1 |  | 2027-01-31 | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Not started
DOC-10 | India CTR reference-pattern report | 2.4 | Solution Architect | v0.1 |  | 2027-01-31 | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Not started
DOC-11 | Target architecture & security design (Gate 2) | 2.6 | Solution Architect | v0.1 |  | 2027-02-28 | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Not started
DOC-12 | Business requirements document — per country | 3.1 | Business Analyst | v0.1 |  | 2027-03-31 | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Not started
DOC-13 | Functional & technical specification (solution design) | 3.2 | Solution Architect | v0.1 |  | 2027-04-30 | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Not started
DOC-14 | Data-privacy & residency assessment (DPIA) per jurisdiction | 3.3 | Security Lead | v0.1 |  | 2027-03-31 | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Not started
DOC-15 | Integration approval & security review record | 3.4 | Integration Lead | v0.1 |  | 2027-04-30 | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Not started
DOC-16 | Data-mapping specification & account-mapping lists | 5.1 / 5.2 | Data Specialist | v0.1 |  | 2027-06-30 | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Not started
DOC-17 | Reconciliation control design (TB / GL) | 6.5 | Data Specialist | v0.1 |  | 2027-09-30 | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Not started
DOC-18 | Test strategy & UAT pack (scripts, entry / exit criteria) | 12.1 | QA Lead | v0.1 |  | 2028-03-31 | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Not started
DOC-19 | Cutover & hypercare plan — per wave | 13.1 | Programme Manager | v0.1 |  | 2028-04-30 | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Not started
DOC-20 | Training & change-enablement pack | 13.1 | Change / Training Lead | v0.1 |  | 2028-04-30 | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Not started
DOC-21 | Operational runbook & handover to run | 13.7 | DevOps Engineer | v0.1 |  | 2028-10-31 | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Not started
SIGN-OFF SUMMARY
Documents in register |  |  | Fully signed off |  |  | In review |  |  | Not started |  |  | Overdue vs review date |  |  | Country sign-offs obtained
21 |  |  | 0 |  |  | 0 |  |  | 21 |  |  | 0 |  |  | 0 of 126
SIGN-OFF PROTOCOL
Who signs |  | Each country tax practice lead signs for their jurisdiction; Intela PMO signs for product and platform impact; Silverfin signs where the document commits them to API access, configuration or support.
Turnaround |  | Documents are circulated with a review-due date (calculated in this register). Ten working days for review; silence is not consent — the status stays Pending until a named approver responds.
Escalation |  | Any document still Pending five working days after its review date is escalated to the programme sponsor and logged as an issue against the relevant phase gate.
Version control |  | Update the version cell each time a document is re-circulated and reset the country columns to Pending. Only the version recorded here is the approved one.
Gate link |  | Gate 1 (DOC-06), Gate 2 (DOC-11) and the phase-3 sign-off gate (DOC-12 to DOC-15) cannot be passed until every applicable column on those rows reads Signed.

## UAT
USER ACCEPTANCE TESTING — PER REGION
Step 4 of the regional approach. Readiness per country, the scenario library, and the execution log that feeds both.
A. UAT READINESS & OUTCOME BY COUNTRY
Country | Wave | UAT window | Environment ready | Test data ready | SME assigned | Scenarios run | Passed | Failed / blocked | UAT status | Sign-off date
South Africa | Wave 1 | 01 Apr 28 – 30 Apr 28 | Not ready | Not ready |  | 0 | 0 | 0 | Not started
Nigeria | Wave 2 | 01 Jun 28 – 30 Jun 28 | Not ready | Not ready |  | 0 | 0 | 0 | Not started
Kenya | Wave 2 | 01 Jun 28 – 30 Jun 28 | Not ready | Not ready |  | 0 | 0 | 0 | Not started
Ghana | Wave 3 | 01 Aug 28 – 31 Aug 28 | Not ready | Not ready |  | 0 | 0 | 0 | Not started
Tanzania | Wave 3 | 01 Aug 28 – 31 Aug 28 | Not ready | Not ready |  | 0 | 0 | 0 | Not started
Uganda | Wave 3 | 01 Aug 28 – 31 Aug 28 | Not ready | Not ready |  | 0 | 0 | 0 | Not started
B. UAT SCENARIO LIBRARY — run this set in every country
ID | Module | Scenario | Expected result |  | Priority
UAT-01 | Client & engagement | Create a client in Intela | Client appears in Silverfin with matching entity details and identifiers |  | Critical
UAT-02 | Client & engagement | Update client details in Silverfin | Change is reflected in Intela within the agreed SLA |  | High
UAT-03 | Client & engagement | Add a user to an engagement team | User synchronises to both platforms with the correct role |  | Medium
UAT-04 | Client & engagement | Link an engagement to a Silverfin period | Period linkage is correct and the engagement opens against the right year |  | High
UAT-05 | Trial balance & GL | Push a trial balance from Intela to Silverfin | TB totals reconcile to source; no rounding or sign errors |  | Critical
UAT-06 | Trial balance & GL | Apply the local chart-of-accounts mapping | Every account maps to the correct Silverfin account per the mapping list |  | Critical
UAT-07 | Trial balance & GL | Push a TB containing an unmapped account | Sync raises a visible exception; nothing posts silently |  | Critical
UAT-08 | Trial balance & GL | Synchronise general ledger detail for a period | GL lines synchronise completely and tie back to the TB |  | High
UAT-09 | Trial balance & GL | Re-run the same TB push | No duplicate balances are created; the prior load is superseded |  | High
UAT-10 | Documents | Upload a document in Intela | Document appears in Silverfin with metadata and taxonomy intact |  | High
UAT-11 | Documents | Run a Live Export from Silverfin | Exported document lands in the correct Intela engagement file |  | High
UAT-12 | Documents | Upload a new version of an existing document | New version supersedes the old one and version history is retained |  | Medium
UAT-13 | Documents | Reach a document's retention date | Retention rule applies as configured for that jurisdiction |  | Medium
UAT-14 | Status | Change engagement status in Intela | Silverfin status updates within the agreed SLA |  | High
UAT-15 | Status | Change engagement status in Silverfin | Intela status updates within the agreed SLA |  | High
UAT-16 | Status | Make conflicting status changes in both platforms | Conflict resolves per the agreed system-of-record rule and is logged |  | Critical
UAT-17 | Comments & to-do | Raise a review note in Silverfin | Note appears as a comment in Intela against the same engagement |  | Medium
UAT-18 | Comments & to-do | Assign a to-do to a preparer | To-do synchronises with the correct assignee and due date |  | Medium
UAT-19 | Workflow | Trigger an event-based automation rule | The expected downstream action runs once, in the right order |  | High
UAT-20 | Monitoring | Force a sync failure | An alert is raised and the failure is visible on the monitoring dashboard |  | Critical
UAT-21 | Monitoring | Review the audit trail for a synced record | User, timestamp and payload are recorded and retrievable |  | High
UAT-22 | Security | Attempt access from outside the engagement team | Access is refused and the attempt is logged |  | Critical
UAT-23 | Privacy | Confirm where country records are stored | Records remain in the approved region for that jurisdiction |  | Critical
C. UAT EXECUTION LOG — one row per scenario per country
Country | Scenario ID | Module | Tester | Planned date | Executed date | Result | Defect ref | Severity | Retest result | Comments
Not run
Not run
Not run
Not run
Not run
Not run
Not run
Not run
Not run
Not run
Not run
Not run
Not run
Not run
Not run
Not run
Not run
Not run
Not run
Not run
Not run
Not run
Not run
Not run
Not run
Not run
Not run
Not run
Not run
Not run
Not run
Not run
Not run
Not run
Not run
Not run
Not run
Not run
Not run
Not run
Not run
Not run
Not run
Not run
Not run
Not run
Not run
Not run
Not run
Not run
Not run
Not run
Not run
Not run
Not run
Not run
Not run
Not run
Not run
Not run
Not run
Not run
Not run
Not run
Not run
Not run
Not run
Not run
Not run
Not run
Not run
Not run
Not run
Not run
Not run
Not run
Not run
Not run
Not run
Not run
Entry criteria: environment and test data ready · scenario library agreed with the country practice · SMEs named and available. Exit criteria: every Critical and High scenario passed · no open Critical or High defects · country practice lead signs off in column K and dates column L.

## Risks
RISK REGISTER
Likelihood × impact, each scored 1–5. Score 15+ high · 8–14 medium · below 8 low.
ID | Category | Risk | L | I | Score | Rating | Mitigation / response | Owner | Status
R-01 | Vendor / Access | SyncAPI access not granted or delayed by Silverfin, blocking TB / GL synchronisation | 5 | 5 | 25 | High | Raise a formal access request during discovery; secure a vendor SLA and escalation path; design a fallback TB import | Integration Lead | Open
R-02 | Technical | Comments / To-Do (Remarks) APIs unsupported or limited bi-directionally | 4 | 3 | 12 | Medium | Early validation spike in Technical Discovery; agree a one-way fallback design if constrained | Integration Engineer | Open
R-03 | Data | Trial-balance and chart-of-accounts mapping inconsistencies across the six countries | 4 | 4 | 16 | High | Account-mapping lists; transformation rules; reconciliation controls; per-country validation | Data Specialist | Open
R-04 | Compliance | Data residency and privacy differences (POPIA, NDPA, Kenya / TZ / UG / GH DPAs) | 3 | 5 | 15 | High | Data Protection Impact Assessment; regional hosting; per-jurisdiction legal review | Security Lead | Open
R-05 | Scope | Country-specific statutory and tax requirements expand scope | 4 | 3 | 12 | Medium | Change control; country prioritisation; MVP-first per market | Programme Manager | Open
R-06 | Resource | Scarcity of Silverfin / Intela integration skills | 4 | 4 | 16 | High | Early staffing; vendor enablement; structured knowledge transfer; reuse of the architecture | Programme Manager | Open
R-07 | Dependency | Intela Integration Agent maturity or feature limitations | 3 | 4 | 12 | Medium | Proof of concept; India CTR reference; vendor engagement on the roadmap | Integration Lead | Open
R-08 | Schedule | 24-month multi-country rollout slips against plan | 4 | 4 | 16 | High | Wave-based rollout; critical-path management; phase-gate buffers; hypercare windows | Programme Manager | Open
R-09 | Performance | API rate limits or performance degradation at scale | 3 | 3 | 9 | Medium | Batching and throttling; caching; load and volume testing before go-live | Solution Architect | Open
R-10 | Change | Low practitioner adoption across countries | 3 | 4 | 12 | Medium | Change management; training; country champions; phased cut-over | Change / Training Lead | Open
R-11 | Security | Credential and secret sprawl across environments and countries | 3 | 4 | 12 | Medium | Central vault; rotation; least privilege; secrets scanning in CI/CD | Security Lead | Open
R-12 | Quality | Bi-directional sync conflicts — source-of-truth ambiguity | 4 | 4 | 16 | High | Define the system of record per data domain up front (see open question Q-01) | Solution Architect | Open
R-13 | Vendor | Silverfin or Intela roadmap changes mid-programme | 2 | 3 | 6 | Low | Vendor governance; versioned APIs; contract change control | Programme Manager | Open
R-14 | Financial | Budget overrun on per-country customisation | 3 | 4 | 12 | Medium | Reusable architecture; standardisation; stage-gated funding | Programme Manager | Open
R-15 | Operational | Silent integration failures without monitoring | 3 | 4 | 12 | Medium | Observability, alerting and audit trail delivered in phase 11 | DevOps Engineer | Open
SCORING GUIDE
1 – 7 |  | Low | Accept and monitor at the fortnightly review.
8 – 14 |  | Medium | Named owner and a dated response; reviewed monthly.
15 – 25 |  | High | Escalate to the sponsor within 48 hours; reviewed at every checkpoint.

## Dependencies
DEPENDENCIES, ASSUMPTIONS & OPEN QUESTIONS
What the programme relies on but does not control, and what must be resolved during discovery.
ID | Type | Dependency | Description | Needed by | Owner | Status
D-01 | Vendor | Silverfin SyncAPI access | Access to SyncAPI to synchronise trial balance and general ledger — the critical-path dependency | Phase 6 (by M8) | Integration Lead | Open
D-02 | Vendor | Intela Integration Agent | Availability and configuration of the strategic integration mechanism | Phase 4 (by M4) | Integration Lead | Open
D-03 | Internal | India CTR reference | Access to India CTR documentation and team for the reference architecture | Phase 2 (by M3) | Solution Architect | Open
D-04 | Vendor | Silverfin API credentials | API credentials per country / firm environment | Phase 4 (by M5) | Security Lead | Open
D-05 | Internal | Country SME availability | Part-time tax SMEs for all six countries throughout the programme | Phase 1 onward | Country Leads | Open
D-06 | Internal | Cloud tenancy & environments | Provisioning of dev / test / UAT / prod meeting data-residency needs | Phase 4 (by M4) | DevOps Engineer | Open
D-07 | Internal | Data-privacy sign-off | Per-jurisdiction privacy approval (POPIA, NDPA and others) | Phase 3 & 11 | Security Lead | Open
D-08 | Internal | Client CoA & mapping data | Charts of accounts and mapping source data per client | Phase 5–6 (by M7) | Data Specialist | Open
D-09 | Vendor | Silverfin licensing | Confirmed Silverfin licensing for each country in scope | Phase 1 (by M3) | Programme Manager | Open
D-10 | Internal | Change & training resource | Change-management and training capacity for rollout | Rollout (M18+) | Change / Training Lead | Open
PLANNING ASSUMPTIONS
ID | Assumption |  |  | Impact if invalid | Owner | Status
A-01 | Silverfin SyncAPI is available under Deloitte licensing and access will be granted |  |  | Blocks TB / GL sync; re-plan phase 6 | Integration Lead | To confirm
A-02 | The Intela Integration Agent is the strategic integration mechanism |  |  | Architecture rework | Solution Architect | To confirm
A-03 | The India CTR integration is available as a reference pattern |  |  | Slower discovery; more design effort | Solution Architect | To confirm
A-04 | Cloud tenancy can meet each country's data-residency needs |  |  | Hosting redesign; compliance risk | Security Lead | To confirm
A-05 | Country SMEs are available part-time throughout the programme |  |  | Requirements and rollout delays | Programme Manager | To confirm
A-06 | Bi-directional sync is required and the system of record is confirmed per data domain |  |  | Sync conflicts (see R-12) | Solution Architect | To confirm
A-07 | Budget and resourcing are approved for a 24-month programme |  |  | Scope or timeline reduction | Sponsor | To confirm
OPEN QUESTIONS — to resolve in discovery
ID | Question |  |  | Why it matters | Owner | Status
Q-01 | Source of truth — which platform is the system of record for each data domain? |  |  | Determines bi-directional sync design and conflict rules | Solution Architect | Open
Q-02 | SyncAPI access — how is it provisioned; what are the timelines, cost and per-country implications? |  |  | Critical-path dependency for TB / GL | Integration Lead | Open
Q-03 | Comments API — are Remarks / Comments and to-do fully supported bi-directionally? |  |  | Confirms phase 9 scope and fallback | Integration Engineer | Open
Q-04 | TB import APIs — confirmed endpoints, formats and volume limits? |  |  | Drives TB integration design and performance | Data Specialist | Open
Q-05 | Country-specific requirements — statutory and tax differences affecting mapping? |  |  | Scope, mapping and rollout sequencing | Country SMEs | Open
Q-06 | Rollout priorities — confirm country sequencing and the South Africa pilot? |  |  | Locks the wave plan and schedule | Programme Manager | Open

## Country Rollout
COUNTRY ASSESSMENT & ROLLOUT WAVES
Readiness across the six markets and the wave sequencing that follows from it.
Country | Practice maturity | Silverfin adoption | Data-privacy regime | Complexity | Wave | Priority | Notes
South Africa | High | High | POPIA | Medium | Wave 1 | Pilot | Largest Deloitte Africa tax practice; strongest Silverfin base; closest to the target operating model
Nigeria | High | Medium | NDPA / NDPR | High | Wave 2 | High | Strong local team; active Nigeria Tax Act 2025 work; high statutory complexity
Kenya | Medium | Medium | Kenya DPA 2019 | Medium | Wave 2 | High | East-Africa hub; regional coordination point
Ghana | Medium | Low | DPA 2012 | Medium | Wave 3 | Medium | West-Africa rollout; requires enablement uplift
Tanzania | Low | Low | PDPA 2022 | Medium | Wave 3 | Medium | Lower current adoption; standardise on the established pattern
Uganda | Low | Low | DPPA 2019 | Medium | Wave 3 | Medium | Lower current adoption; leverage East-Africa learnings
ROLLOUT WAVES
Wave | Countries | Months | Scope |  |  | Entry criteria | Exit / go-live criteria
Wave 0 | Build & pilot preparation (all countries) | M1–M17 | Foundation layer plus all integration modules (client, TB / GL, documents, status, comments, workflow, monitoring) |  |  | Charter approved; SyncAPI access and architecture baseline confirmed | All modules pass integration testing; UAT scripts ready
Wave 1 | South Africa (pilot) | M18–M19 | Full solution pilot in the most mature market |  |  | Wave 0 complete; monitoring and audit accepted; SA environment ready | SA in production; reconciliation clean; hypercare exit met
Wave 2 | Nigeria, Kenya | M20–M21 | Country configuration, UAT and go-live for NG and KE |  |  | Wave 1 stabilised; country requirements and mappings confirmed | NG and KE in production; hypercare exit met
Wave 3 | Ghana, Tanzania, Uganda | M22–M24 | Country configuration, UAT and go-live for GH, TZ and UG; programme closure |  |  | Wave 2 stabilised; enablement and training complete | All six countries live; benefits realised; handover to run